EduGenie — Gemini Powered Learning Assistant

Project Planning Phase — Product Backlog, Sprint Planning, Stories & Estimation

| Field | Details |
| --- | --- |
| Date | 23/09/2026 |
| Team ID | SWTID-2026-4128 |
| Project Title | EduGenie — Gemini Powered Learning Assistant |
| Team Size | 4 |
| Team | Team Leader: Prawin A K ¦ Team Members: Suganesh Govindaraj ¦ Thamaraiselvan K ¦ Thamaraiselvan Eswaran |

# Product Backlog

| Sprint | Epic / Task | Story ID | Story | Points | Priority | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 | Project setup | US-1 | Create Python environment, FastAPI app, configuration, and health check | 5 | High | Prawin A K |
| Sprint 1 | Frontend shell | US-2 | Create responsive HTML/CSS/JS interface | 6 | High | Suganesh Govindaraj |
| Sprint 1 | Q&A and explanation | US-3 | Implement question answering and topic explanation endpoints | 8 | High | Thamaraiselvan K |
| Sprint 2 | Summarization | US-4 | Implement bounded text input and summary generation | 6 | High | Thamaraiselvan Eswaran |
| Sprint 2 | Quiz generation | US-5 | Generate and validate exactly 3 MCQs with 4 options | 10 | High | Prawin A K |
| Sprint 3 | Learning paths | US-6 | Implement structured learning recommendations | 7 | High | Suganesh Govindaraj |
| Sprint 3 | AI service abstraction | US-7 | Implement GeminiService, DemoService, prompts, and error handling | 10 | High | Thamaraiselvan K |
| Sprint 4 | Testing and documentation | US-8 | Add pytest tests, README, API examples, and final report | 8 | Medium | All members |

# Sprint Plan

| Sprint | Duration | Planned Outcome |
| --- | --- | --- |
| Sprint 1 | 5 days | Runnable FastAPI app, UI shell, health check, Q&A, explanation |
| Sprint 2 | 5 days | Summary and quiz features with validation |
| Sprint 3 | 5 days | Learning path, Gemini integration, demo mode, error handling |
| Sprint 4 | 4 days | Automated tests, documentation, review, and release package |

# Definition of Done

Feature has a route, input validation, service call, and response model.

Browser UI can invoke the feature and display success or error output.

Demo mode works without an API key.

Automated tests cover the endpoint and important response constraints.

README explains setup, environment variables, run commands, and API examples.